MC Critical Path - [TITLE OF MC] 
(Cabinet Committee – [Date])

Cabinet Affairs Analyst: 				 Main Program Contact:

T-Minus timeline indicates working back from the submission deadline

Day = business day 		Week = 5 business days

Legend:              Cabinet Affairs Responsibility

| Step | Key Step | Expected Timing | Expected Date | Date Completed |
| --- | --- | --- | --- | --- |
| 1.0 LAUNCH OF MC |  |  |  |  |
| 1.1 | Initial Meeting with Cabinet Affairs to discuss roles and responsibilities, timelines, requirements and to establish working group contacts | More than 11 weeks prior to the PCO Delivery Date |  |  |
| 1.2 | Kick-off meeting with key departmental contacts and key OGD contacts |  |  |  |
| 2.0 DEVELOPMENT OF INITIAL DRAFT |  |  |  |  |
| 2.1 | Drafting MC | As early as possible |  |  |
|  | Presentation at Deputy Minister Policy Committee (when required) |  |  |  |
|  | Ministerial briefing(s) |  |  |  |
|  | Informal Central Agencies check in |  |  |  |
|  | Consultation with key departmental contacts and/or implicated OGDs |  |  |  |
|  | Share early draft of MC with Deputy Minister’s Office |  |  |  |
| 2.2 | Quality Control of draft MC by Cabinet Affairs | # T - Day 52 |  |  |
| 2.3 | Submit draft MC (including annexes) and draft Due Diligence Tool to PCO | # T - Day 51 |  |  |
|  | Circulation of draft MC internally by Cabinet Affairs. (MINO, DMO, CFOB, Legal Services, PASRB, Parliamentary Affairs) |  |  |  |
| 2.4 | Lead Branch to incorporate any comments | # T - Day 50-43 |  |  |
| 2.5 | Translation of MC (Arranged by Lead Branch) |  |  |  |
| 3.0 FINALIZATION OF MC |  |  |  |  |
| 3.1 | Quality control of revised draft by Cabinet Affairs | # T - Day 42-41 |  |  |
| 3.2 | Lead Branch to seek ADM approval of revised draft MC and circulate to Central Agencies (PCO, TBS, Finance) | # T - Day 41 |  |  |
| 3.3 | Submit draft MC to Central Agencies (PCO, TBS, Finance) (copy to DMO) | # T - Day 40 |  |  |
| 3.4 | Circulation of draft MC internally by Cabinet Affairs. (MINO, DMO, CFOB, Legal Services) |  |  |  |
| 3.5 | Central Agencies Meeting | # T – Day 35 |  |  |
| 3.6 | Revisions to draft MC and due diligence tool | # T - Day 34-33 |  |  |
| 3.7 | Interdepartmental Meeting (Organized by Cabinet Affairs, chaired by Lead Branch) | # T - Day 32 |  |  |
| 3.8 | Final approval in writing of Communications Strategy and Parliamentary Strategy | # T- Day 31 |  |  |
| # 4.0 FINAL APPROVALS completed by Cabinet Affairs # ** For each approval stage, any ensuing changes to the MC will require quality assurance of the format by Cabinet Affairs. |  |  |  |  |
| 4.1 | Lead Branch delivers Final MC (paper & electronic version) to Cabinet Affairs. | # T-Day 28 |  |  |
| 4.2 | Final Revisions to MC + Quality Control by Cabinet Affairs | # T-Day 27 |  |  |
| 4.3 | Final MC Package to Lead DG and Lead ADM for approval (prepared by Cabinet Affairs) | # T - Day 26-24 |  |  |
| 4.4 | Final MC Package to CFOB and Legal Services for final attestation. | # T - Day 23 |  |  |
| 4.5 | Final MC Package to the COO and/or supporting DM for approval (when required) | # T- Day 20 |  |  |
| 4.6 | Final MC Package to the Deputy Minister for approval. | # T - Day 15 |  |  |
| 4.7 | Final MC Package to the responsible Minister for approval. | # T - Day 10 |  |  |
| 4.8 | Ministerial Signature | # T- Day 1 |  |  |
| 5.0 DELIVERY TO PCO BY CABINET AFFAIRS |  |  |  |  |
| 5.1 | Submission of Final Bilingual Documents to PCO by 10AM. Exactly 9 full business days prior to the Committee Date. | T - 0 |  |  |

Reminder:

Lead Branch will be required to prepare briefing materials, including speaking points and Q&As to support the Minister’s presentation at Cabinet Committee. The Lead Branch will route these briefing materials in a separate docket for approval by ADM, DM, and Minister.