## Critical Path TB Sub - EN
Treasury Board (TB) Submission Name CRITICAL PATH As at 2018-XX-XX (subject to change)
Steps |  | Duration | Date | Action Item | Responsible Unit | Comments / Standards
Drafting (31 working days) | 1 | N/A |  | Internal kick-off meeting. | SCU | Submission Control Unit (SCU) to organize internal meeting with Program and various stakeholders.
| 2 | N/A |  | Kick-off meeting with Treasury Board Secretariat (TBS). | SCU | SCU to organize planning session with TBS analyst(s).
| 3 | 21 working days (1 month) |  | Drafting of TB submission. | Program / FMA / SCU / EPMO | Program (pen holder) to work on preliminary draft of the TB submission in collaboration with FMA, SCU, EPMO and Internal Stakeholders (Legal, Evaluation, GBA, etc.). Approximately 1 month to draft preliminary TB submission and project documents, if applicable. Standard: 21 working days
| 4 | 10 working days |  | Solid preliminary draft shared with SCU for submission to stakeholders for review. | SCU | Standard: 5 working days
| 5 |  |  | First complete internal draft to SCU for review | SCU | Stakeholder comments integrated by Program. Typically 1-3 internal drafts are shared between Program and SCU. Standard: 5 working days
TBS Review Cycle (42 working days) | 6 | 15 working days |  | First Official Draft of TB submission to TBS. | SCU | Standard TBS Review: 15 working days for First Official Draft. Subsequent drafts TBD depending on situation. Program to submit first official draft to Translation. Note that the First Official Draft to TBS must: - be reviewed by stakeholders; - be supported by Deputy Chief Financial Officer (DCFO); - include all appendices; and - have all proper authorities in place (project, program, policy, etc.). Please refer to note (1) below for TBS Service and Quality Standards.
| 7 | 7 working days |  | Program area updates first official draft based on TBS comments. SCU reviews comments prior to sending second official draft to TBS. | Program / SCU | Draft should be shared with stakeholders, as required depending on TBS's comments, to accelerate the approval process of final version. All changes are reviewed by SCU.
| 8 |  |  | Chief Financial Officer (CFO) Attestation. | FMA | CFO Attestation (long form) prepared by FMA; and will require approval by Program Assistant Deputy Minister's (ADM). (The CFO Attestation is not required for Authorities Instrument). CFO Attestation will be signed during the final approval process.
| 9 | 10 working days |  | Second Official Draft to TBS. Briefing with CFO, Deputy Minister's (DM) Office/Chief Operating Officer (COO) and Minister's Office (MinO) by Program ADM. | SCU / Program | The Second Official Draft incorporates comments following a full review by TBS Policy Centres. Program is to highlight all changes from first official draft and re-submit to Translation. This draft is shared with MinO (clean version). SCU to deliver docket to DMO/COO and MinO. Program to organize a meeting with CFO, DM's Office/COO and MinO to brief on the TB submission; and prepare the Note to MinO (with SCU guidance and review) to accompany the Second Official Draft. Docket to be routed through Program ADM and CFO. All following versions sent up need track changes and highlights, and must follow this same process. This draft is also shared with stakeholders for a second review of their content prior to the "proceed to signature" from TBS is received.
| 10 | 5 working days |  | Program area updates second draft based on TBS comments. SCU reviews comments prior to sending third official draft to TBS. | Program / SCU | Draft should be shared with stakeholders, as required depending on TBS's comments, and to accelerate the approval process of final version. All changes are reviewed by SCU.
| 11 | 5 working days |  | Third Official Draft to TBS. | SCU | The Third Official Draft incorporates TBS comments from second official draft. Program is to further highlight all changes from second official draft and re-submit to Translation.
| 12 |  |  | "Proceed to signature" from TBS. | SCU | SCU advises all stakeholders when TBS provides green light to proceed to signature. Program to ensure final draft is translated.
Quality Control (9 working days) | 13 | 3 working days |  | Final updates of TB submission including translation and QC. | Program | Program Director General to confirm translation and QC are completed. Program will also need to prepare the Memo to Minister for final approval (SCU to provide guidance and review). Standard: Up to 3 working days
| 14 | 6 working days |  | Final fully translated TB submission to SCU for final QC. | SCU | Standard: Up to 6 working days
Approvals (19 working days) | 15 | 2 working days |  | Official Docket to Program ADM for approval. | Program | Standard: 2 working days
| 16 | 3 working days |  | Official Docket to Legal Services for approval (includes approval from Program ADM). | Program | Signature required for Legal Services approval. Standard: 3 working days
| 17 | 2 working days |  | Official Docket to SCU for CFO's approval (includes approvals from Program ADM and Legal Services). | SCU | Standard: 2 working days
| 18 | 5 working days |  | Official Docket to DMO for DM's approval (or COO for Service Canada). | SCU | Additional working days may be required when both COO and DM need to approve. Standard: 5 working days
| 19 | 7 working days |  | Official Docket to MinO for Minister's approval. | SCU | Standard: 7 working days
Delivery (17 working days) | 20 | 17 working days |  | Final approved package delivered to TBS. | SCU | Standard: 17 working days before TB Meeting Date (delivered by noon on a Tuesday).
TB Meeting Date
It takes approximately 118 working days (or 5½ months) to develop a Treasury Board submission.
Revised: May 28, 2018
(1) TBS Service and Quality Standards to Support TB Submission Reviews

## Critical Path FAI - EN (hidden)
Financial Authorities Instrument (FAI) Name CRITICAL PATH As at 2018-XX-XX (subject to change)
Steps |  | Duration | Date | Action Item | Responsible Unit | Comments / Standards
Drafting (21 working days) | 1 | N/A |  | Internal kick-off meeting. | SCU | Submission Control Unit (SCU) to organize internal meeting with Program and various stakeholders.
| 2 | N/A |  | Kick-off meeting with Treasury Board Secretariat (TBS). | SCU | SCU to organize planning session with TBS analyst(s).
| 3 | 15 working days |  | Drafting of the FAI. | Program / FMA / SCU / EPMO | Program (pen holder) to work on preliminary draft of the FAI in collaboration with FMA, SCU, EPMO and Internal Stakeholders (Legal, EPMO, GBA, etc.). Approximately 3 weeks to draft preliminary FAI and project documents, if applicable. Standard: 15 working days
| 4 | 3 working days |  | Solid preliminary draft shared with SCU for submission to stakeholders for review. | SCU | Standard: 3 working days
| 5 | 3 working days |  | First complete internal draft to SCU for review. | SCU | Stakeholder comments integrated by Program. Typically 1-3 internal drafts are shared between Program and SCU. Standard: 3 working days
TBS Review Cycle (40 working days) | 6 | 15 working days |  | First Official Draft of FAI to TBS. | SCU | Standard TBS Review: 15 working days for First Official Draft. Subsequent drafts TBD depending on situation. Program to submit first official draft to Translation. Note that the First Official Draft to TBS must: - be reviewed by stakeholders; - be supported by Deputy Chief Financial Officer (DCFO); - include all 4 required appendices; and - have all proper authorities in place (project, program, policy, etc.). Please refer to note (1) below for TBS Service and Quality Standards.
| 7 | 5 working days |  | Program area updates first draft based on TBS comments. SCU reviews comments prior to sending second official draft to TBS. | Program / SCU | Draft should be shared with stakeholders, as required depending on TBS's comments, to accelerate the approval process of final version. All changes are reviewed by SCU.
| 8 | 10 working days |  | Second Official Draft to TBS. Briefing with Chief Financial Officer (CFO), Deputy Minister's (DM) Office/Chief Operating Officer (COO) and Minister's Office (MinO) by Program ADM. | SCU / Program | The Second Official Draft incorporates comments following a full review by TBS Policy Centres. Program is to highlight all changes from first official draft and re-submit to Translation. This draft is shared with MinO (clean version). SCU to deliver docket to DMO/COO and MinO. Program to organize a meeting with CFO, DM's Office/COO and MinO to brief on the FAI; and prepare the Note to MinO (with SCU guidance and review) to accompany the Second Official Draft. Docket to be routed through Program ADM and CFO. All following versions sent up need track changes and highlights, and must follow this same process. This draft is also shared with stakeholders for a second review of their content prior to the "proceed to signature" from TBS is received.
| 9 | 5 working days |  | Program area updates second official draft based on TBS comments. SCU reviews comments prior to sending third official draft to TBS. | Program / SCU | Draft should be shared with stakeholders, as required depending on TBS's comments, and to accelerate the approval process of final version. All changes are reviewed by SCU.
| 10 | 5 working days |  | Third Official Draft to TBS. |  | The Third Official Draft incorporates TBS comments from second official draft. Program is to further highlight all changes from second official draft and re-submit to Translation.
| 11 |  |  | "Proceed to signature" from TBS. | SCU | SCU advises all stakeholders when TBS provides green light to proceed to signature. Program to ensure final draft is translated.
Quality Control (5 working days) | 12 | 2 working days |  | Final updates of FAI including translation and Quality Control (QC). | Program | Program Director General to confirm translation and QC are completed. Program will also need to prepare the Memo to Minister for final approval (SCU to provide guidance and review). Standard: Up to 2 working days
| 13 | 3 working days |  | Final fully translated FAI to SCU for final QC. | SCU | Standard: Up to 3 working days
Approvals (12 working days) | 14 | 1 working day |  | Official Docket to Program ADM for approval. | Program | Standard: 1 working day
| 15 | 2 working days |  | Official Docket to Legal Services for approval (includes approval from Program ADM). | Program | Signature required for Legal Services approval. Standard: 2 working days
| 16 | 1 working day |  | Official Docket to SCU for CFO's approval (includes approvals from Program ADM and Legal Services). | SCU | Standard: 1 working day
| 17 | 3 working days |  | Official Docket to DMO for DM's approval (or COO for Service Canada). | SCU | Additional working days may be required when both COO and DM need to approve. Standard: 3 working days
| 18 | 5 working days |  | Official Docket to MinO for Minister's approval. | SCU | Standard: 5 working days
Delivery (17 working days) | 19 | 17 working days |  | Final approved package delivered to TBS. | SCU | Standard: 17 working days before TB Meeting Date (delivered by noon on a Tuesday).
TB Meeting Date
It takes approximately 95 working days (or 4½ months) to develop a FAI.
Revised: May 24, 2018
(1) TBS Service and Quality Standards to Support TB Submission Reviews